AIHA-NCS Developing World Outreach Initiative

Meeting Minutes

Date: January 13th, 2022

Time: 4:30 pm – 5:30 pm PST, teleconference call

Attendees: Richard Hirsh, Karen Gunderson, Garrett Brown, Carina Kouyoumji, Ted Zellers, Jeff Dalhoff

- Welcome attendees by Chairperson Rich Hirsh

- DWOI members met in December to review project ratings and select those technical projects and training workshops that either DWOI or MHSSN will sponsor in 2022 and selected the subset of 3 trainings that the ACGIH FOHS grant ($1500) will cover: SRS in Bangladesh (Risk Assessment for Tannery Workers); IOHSAD in the Philippines (Building Worker led OSH Committees); and HomeNet in Pakistan (Homebased and Domestic Workers OHS Issues). In total, DWOI will fund 4 technical projects and 7 training workshops in 2022. A full listing of the sponsored projects and their funding sources accompany these minutes.

- Rich and Garrett submitted the technical projects and training workshop proposals that DWOI/MHSSN could not fund to the AIHA microgrants committee in December before the 12/31 deadline for their evaluation. These projects include the following NGO technical projects: SRS in Bangladesh (stone crushing); CBBRC in the Philippines (Jeepney Drivers OHS Risks during Covid-19); and PROBICOU in Uganda (Mercury exposure during gold mining) as well as the following NGO training workshops: MLPC in India (Silicosis in mine workers) and FTZ in Sri Lanka (Covid Prevention amongst Women Apparel Workers).   No confirmation from AIHA was received for those submittals and Garrett contacted AIHA for follow-up after the DWOI meeting.

- Garrett reported that all DWOI/MHSSN funds have been successfully wire transferred through banks to their respective NGO recipients. Carina raised the issue of exploring alternative money transfer options (Paypal, Western Union, etc) to avoid the steep bank transfer fees of ~$1000 incurred, which have been covered by the MHSSN.

- Technical advisors for the technical projects were identified: Perry Gottesfeld will serve as technical project advisor for the Casa Cem lead paint project in Mexico, David Kahane has agreed to serve as technical project advisor for the welding fume study by CEPHED in Nepal,  Barbara Cohrssen and Tessa Landgraf will serve as technical advisors for the CIVIDEP garment manufacturing project in India, and Ted Zellers will serve as technical advisor for the UNETMAC pesticide project in Uganda. Attempts to reach Professor Andrea Rother at the University of Capetown to assist as a technical advisor for the pesticide project were unanswered.

- Completed technical projects and training workshops have been posted to the aiha-ncs.org website.

- Technical Project Updates

  - CIVADEP in India on female workers in the leather footwear manufacturing industrial sector in Tamil Nadu. Contact: Deepika Rao. Karen G. serving as liaison. Project report now delayed due to pandemic till March 2022

  - The Environics Trust asbestos monitoring project in India has now been completed and the report has been received and is posted on the DWOI website.

- Attached as Appendix 1 is the current status of the previously sponsored training workshops and technical projects collaboratively funded by DWOI, AIHA (microgrants), MHSSN, and WHWB-US since 2019. There are two sets of tables – one set on the completion of the funded projects; and a second set on the funding sources for the 2019-22 approved projects.

- Ted mentioned that Albert Tien and Bert Schiller of WHWB-US are at an early stage of planning to develop OHS curricula for an OHS program in Ethiopia. There may be opportunities for DWOI to collaborate.

- The UC Berkeley School of Public Health PH290 Global OHS course organized by Garrett Brown is now underway and there are 9 students. Several DWOI members will be serving as guest presenters.

- The next meeting is tentatively scheduled on Thursday, March 3rd at 4:30 pm.

- Meeting adjourned at 5:30 pm.

2019/20 Grants for Trainings and Technical Projects

Developing World Outreach Initiative (DWOI), Maquiladora Health & Safety

Support Network (MHSSN), and Workplace Health Without Borders (WHWB)

Training Grants

| Organization/ Country | Funding Source | Target Population/ Topic | Estimated Time of Training | Report/Photos Received |
| --- | --- | --- | --- | --- |
| MSF-WHWB / Bangladesh | WHWB | Scholarships for OHTA course/BOHS exam | Virtual training will be conducted in 2021 | Cancelled due to Covid |
| Cividep / India | MHSSN | Women shoe workers – hazard research | Training completed | Report / photos received |
| Mallarpur Uthnau / India | WHWB | Silicosis – community training | Target: August 2020 | Report /photos received |
| Mallarpur Uthnau / India | DWOI | Silicosis – worker training | Target: August 2020 | Report /photos received |
| CEREAL / Mexico | DWOI | Women electronics workers – OHS/chem hazards | Target: August 2020 | Report /photos received |
| CETIEN / Mexico | DWOI | Electronics workers – OHS/chem hazards | Training completed | Photos received |
| CFO / Mexico | MHSSN | Women maquila workers – gender violence & laws | Training completed | Report/photos received |
| CEISA / Mozambique | WHWB | University OSH program training | Target: October 2020 | Report/photos received |
| IOHSAD / Philippines | MHSSN | Workers’ mental health issues | Training completed | Report received |
| FTZ-GSE union / Sri Lanka | MHSSN | Free Trade Zone workers – ergonomics | Target: September 2020 | Cancelled due to Covid |
| KKU / Thailand | DWOI | Support for university short course on OHS | Target: September 2020 | Cancelled due to Covid |
| CDI / Vietnam | DWOI | Electronics workers – OHS/chem hazards | Training completed | Report /photos received |

Technical Projects

| Organization/ Country | Funding Source | Target Population/ Topic | Estimated Time of Project | Report/Photos Received |
| --- | --- | --- | --- | --- |
| Cividep / India | DWOI | Tea plantation hazard research – cash grant | Research partially completed; | Report / photos received |
| LION / Indonesia |  | Asbestos bulk sampling – cash & donation | Target: August 2020 | Report received, but limited because samples sent to US for analysis were destroyed by Hong Kong authorities; may send samples submitted to Tekmira lab to Forensic |
| JRP / India | DWOI | Silicosis/TB – cash grant | Research completed – report target: October 2020 | Report /photos received |
| American Univ/ Lebanon | DWOI | Hazard sampling at university – donation | Target: November 2020 | Report/photos received |
| CEPHED / Nepal | DWOI | Mercury contamination sampling – cash grant | Report done; Planning on Zoom presentation of findings to local stakeholder; article in July 2020 ANROEV newsletter | Report/photos received |

January 23, 2022

2020/21 Grants for Trainings and Technical Projects

Developing World Outreach Initiative (DWOI), ACGIH Foundation for Occupational Health and Safety (FOHS), and Maquiladora Health & Safety Support Network (MHSSN)

Training Grants

| Organization/ Country | Topic / Target Population | Estimated Date of Training | Report/Photos Received |
| --- | --- | --- | --- |
| SRS / Bangladesh | Risk assessment –Garment factory safety committee members | Training completed | Report and photos received |
| Cividep / India | New OHS laws (2020) – garment workers and union officials | Training completed | Report received |
| Environics Trust / India | OHS awareness – street vendors | Survey completed – training pending (as possible) |  |
| SAVE / India | OHS awareness in dyeing, bleaching and printing – textile workers | September 2021 |  |
| LION / Indonesia | Countering Covid stigma – general industry |  |  |
| CFO / Mexico | New laws on stress and gender violence – maquiladora workers | Mini-workshops and training completed | Report and photos received |
| 3SM / Mozambique | OHS awareness – 3SM members | Training completed | Report pending |
| Home Net / Pakistan | OHS awareness – informal workers | Training completed | Report and photos received |
| WAC / Philippines | Covid prevention – general industry | Sometime Sept-Nov 2021, as possible |  |

Technical Projects

| Organization / Country | Topic / Target Population | Estimated Time of Project Completion | Report/Photos Received |
| --- | --- | --- | --- |
| CIVIDEP / India | OHS hazards for women leather footwear industry | Project underway – data collection Sep-Dec 2021 | Report in March 2022 |
| CEPHED / Nepal | Asbestos hazards for mechanics handling friction products | Research in progress | Report received |
| LEF / Pakistan | OHS hazards for home-based workers | Data collection completed with questionnaire; data of 100 participants completed; 3 in-depth interviews with labor officials completed | Report received |

January 23, 2022